## Open Items Tracker
Category | Item | Status | Priority | Owner | Blocked By | Recommendation / Notes
Pending decision | iGCSE boards — Edexcel International (4CH1) AND Cambridge (0620/0971) | Decided | High | Arshad | — | DECIDED (4 Sep 2026 reply): both boards, confirmed. CLARIFIED (14 Sep 2026): these need two separate topic trees — 4CH1 has 4 broad top-level areas, 0620/0971 has 12 topics, structures don't align. Already reflected in the pilot scaffold's Board Topic Map (two rows, no restructuring needed) and Board Style Profile (rows already existed for both). Effort impact: roughly doubles iGCSE sourcing/tagging work in the pilot — need to confirm with Arshad whether this shifts the pilot timeline.
Pending decision | Content sourcing — move off PMT; use official board sources + AI-rewritten notes | Decided | High | Arshad | — | DECIDED (4 Sep 2026 reply): Arshad signed off — no PMT, official board sources + AI-rewritten notes only.
Pending decision | Webcam / biometric affect sensing | Decided | Medium | Stakeholder | — | DECIDED (4 Sep 2026 reply): Arshad explicit sign-off to exclude webcam/biometric sensing entirely.
Pending decision | A-Level long-form marking — automation level | Decided | High | Stakeholder | — | DECIDED (4 Sep 2026 reply): matches recommendation — AI-assisted with mandatory human review at launch, taper as confidence data builds. v1.0 (21 Sep 2026, D-16): every A-Level long answer reviewed, shown to the student as provisional until confirmed (F-09/F-05). GCSE/iGCSE: exceptions only (D-17).
Pending decision | Voice / oral practice mode — timing | Decided | High | Stakeholder | — | DECIDED, SCOPE CHANGED (4 Sep 2026 reply): Arshad wants voice mode from day 1 if feasible — pulled forward from Phase 3. Confirm whether 'day 1' means pilot or full MVP launch; drives STT/TTS vendor choice and real-time infra timeline now, not later. See row below (STT/TTS vendor).
Pending decision | Gamification depth vs. AADC nudge-technique risk | Decided | Medium | Stakeholder + Compliance | Named compliance reviewer | DECIDED (4 Sep 2026 reply): hold on gamification depth as recommended. Arshad notes cohort is 14+, not under-13 — still worth a compliance pass since AADC applies broadly to any service likely accessed by under-18s, not just under-13s. v1.0 (D-21): badges, streaks and XP moved to Phase 2 and removed from MVP screens.
Pending decision | B2B schools channel — pursue now or defer | Decided | High | Stakeholder | — | DECIDED, OVERRIDES RECOMMENDATION (4 Sep 2026 reply): Arshad wants schools (B2B) and direct-to-consumer (B2C) launched in parallel, not deferred — he explicitly asked what safeguarding needs addressing for this. Safeguarding workstream must start immediately; see new Governance/Legal items below and the delivered safeguarding note.
Pending decision | LLM vendor & data residency | Decided | High | Stakeholder + Compliance/Procurement | — | Name an owner now even if the vendor itself is TBD. Needs an EDU/enterprise DPA, UK/EU residency option, no-training-on-user-data clause. DECIDED (14 Sep 2026, Architecture FINAL v2 #1): Anthropic Claude, direct API. v1.0 (21 Sep, D-15): no personal data sent to any AI vendor — AI Gateway tokenises and redacts every call. Anthropic enterprise DPA still to sign (architecture §7).
Pending decision | Web app vs. native mobile app for MVP | Decided | High | Arshad / Stakeholder | — | DECIDED (4 Sep 2026 reply): both app and web are in the MVP, confirmed explicitly — not web-only. Flag resourcing/timeline impact for native mobile build (see new Technical item below).
Legal / IP | Exam-board licensing for AI-generation use (beyond free teaching-use download) | Open | High | Arshad + Legal | — | Arshad's view (4 Sep 2026 reply): believes there's no issue since schools and other sites already do this, but will check with the boards directly as recommended. Keep OPEN until boards confirm in writing — this is the item most likely to resurface as a real blocker at scale. = Pending item P-3 in Requirements Baseline v1.0.
Legal / IP | Terms, Privacy Policy, Cookie Policy, Safeguarding Policy, GDPR pages | Not started | Medium | Legal / Arshad | — | Footer nav in the brief already assumes these exist (Part 1, Section 5.7). v1.0: screen Shell-10 (legal pages + cookie consent) now designed; policy text still needed from legal.
Legal / IP | UK ICO Age Appropriate Design Code compliance review | Open | High | Compliance | Named reviewer | Covers engagement telemetry, profiling and gamification/nudge design — see brainstorm doc Section 6. Update (4 Sep 2026): ICO has confirmed EdTech products/services are in scope. Needs a formal Data Protection Impact Assessment, high-privacy defaults, no profiling/geolocation by default, and no engagement-maximising nudges — directly shapes the gamification decision already logged above (row 7).
Legal / IP | KCSIE safeguarding alignment | Open | High | Compliance / Murtaza | — | No longer deferred — B2B channel is launching in parallel with consumer, not after. KCSIE 2026 itself binds schools, not us, but school procurement will expect our policies mapped to it. See delivered safeguarding note for the practical checklist.
Commercial | iGCSE and A-Level pricing tiers | Decided | Medium | Arshad | — | DECIDED (4 Sep 2026 reply): same price tier as GCSE for iGCSE and A-Level, no premium.
Commercial | Payment / subscription processor | Decided | Low | Arshad | — | DECIDED (4 Sep 2026 reply): Stripe confirmed.
Commercial | Outcome-metric / before-after data collection plan | Not started | Medium | Product | — | Needed to support the brief's own "transparent, methodology-explained outcome statistics" trust positioning — build it in from day one.
Commercial | Marketing site CMS platform | Open | Low | Arshad | — | Webflow-equivalent suggested in the brief, not confirmed.
Technical | Hosting / cloud provider | Decided | Medium | Murtaza | — | Matters more if Oracle is the chosen DB (licensing cost) vs. MySQL. DECIDED (14 Sep 2026, #2): self-hosted Docker, Hetzner-style. DB is PostgreSQL (#3), so Oracle licensing no longer applies. Open follow-up P-9: whether schools require UK-only hosting (Hetzner is EU).
Technical | Vector store for the RAG / question-generation pipeline | Decided | Medium | Murtaza | — | e.g. pgvector, per the architecture in the brainstorm doc Section 5. DECIDED (14 Sep 2026, #4): pgvector in the same Postgres instance.
Technical | STT / TTS vendor for voice mode | Decided | High | Murtaza | — | Now needed immediately, not Phase 3 — voice mode pulled forward to day 1 per Arshad's 4 Sep reply. Needs a vendor pick and a latency/cost model before the pilot timeline can be finalised. DECIDED (14 Sep 2026, #5): Google Cloud Speech (STT + TTS). v1.0 (D-20): the one vendor path that receives personal data (audio) — separate parent consent (J-06), transcripts kept 30 days (H-09).
Technical | Vision-model vendor for photographed handwritten-answer marking | Decided | Medium | Murtaza | — | Required by brief v3 for all subjects, especially Maths/Science working-out. DECIDED (14 Sep 2026, #6): Claude vision. v1.0: photo header area masked before upload (Baseline §6).
Content scope | Maths, English (Lang & Lit), Physics, Biology — topic scaffolds | Not started | Medium | Content team | Chemistry pilot outcome | Same treatment as the Chemistry scaffold, once the pilot validates the approach.
Content scope | 11+ and A-Level qualification scaffolds | Not started | Medium | Content team | Chemistry pilot outcome | —
Content scope | AI-generated question review staffing | Decided | High | Arshad | Call with Arshad | Arshad's reply (4 Sep 2026): not sure what this covers yet, wants to discuss on a call. Bring options (in-house hire vs. outsourced marking-review panel) to that call. DECIDED (21 Sep 2026, D-18): no routine human review of generated questions — automated 5-check QC, humans handle failures only (E-01). Remaining staffing question is A-Level marking review only — see P-1.
Content scope | Content-team workflow/tooling for completing spec-point tags | Not started | Low | Murtaza / Content lead | — | Process for filling in the yellow "to complete" cells in the pilot scaffold.
Governance | Final sign-off authority | Open | High | Arshad | — | Is it Arshad alone, or someone above him in the client's org? = Pending item P-7 in Requirements Baseline v1.0 — settle on the next call. Needed because change control now requires written, agreed change requests.
Governance | Pilot budget & timeline | Not started | Medium | Arshad | — | Reference point: comparable vertical-MVP AI-tutor builds run roughly $180-320k, a 4-person team, 16 weeks (Fora Soft 2026 build playbook). = Pending item P-6 (Arshad's Round 2 question) — Karsaaz to send estimate before the next call.
Governance | Pilot success criteria | Decided | High | Arshad + Murtaza | — | DECIDED (4 Sep 2026 reply): (1) marking accuracy > 95%; (2) AI generates past-paper-style questions and marks them instantly. Use these as the two headline pilot KPIs. v1.0 (D-19): accuracy measured per marking point against an examiner-marked gold set, by board and question type (Q-01). Gold-set owner = P-2.
Legal / IP | Online Safety Act 2023 — children's access assessment & age-assurance scope check | Open | High | Legal / Murtaza | — | New (4 Sep 2026): voice mode pulled to day 1 plus any student/tutor chat features may bring the platform into scope of OSA children's-safety duties (children's access assessment; if in scope, age assurance + safety/moderation measures on AI-generated and any user-to-user content). Raise with the same lawyer as the exam-board licensing check. = Pending item P-4. Age assurance screen L-05 built behind a swappable interface.
Legal / IP | Safer recruitment — Enhanced DBS + Barred List checks for tutors & marking reviewers | Open | High | Arshad / HR | — | New (4 Sep 2026): not a strict legal requirement for a private platform (a known industry gap), but effectively non-negotiable for school procurement and a strong trust signal for consumer too. Must be in place before schools onboarding starts, given the parallel launch.
Legal / IP | Per-school Data Processing Agreement (DPA) template | Not started | Medium | Legal | — | New (4 Sep 2026): schools act as data controller for pupil data, so each school contract needs its own DPA — an obligation the consumer-only track doesn't carry. Needed before first school signs, not after. = Pending item P-5. DPA signing flow designed in O-07.
Governance | Safeguarding lead + escalation path for parallel B2B/B2C launch | Open | High | Arshad | — | New (4 Sep 2026): Arshad asked directly what safeguarding to address for launching schools and consumer together — see delivered safeguarding note. Needs a named internal safeguarding lead and a clear escalation path for welfare disclosures surfaced through AI chat/voice sessions, ready before schools go live.
Governance | Resend content_model_schema.sql and Project_Open_Items_Tracker.xlsx to Arshad | Open | High | Murtaza | — | New (14 Sep 2026): both files exist and are current, but were only ever saved to the local project folder — never actually sent to Arshad. He flagged this because User_Story_Catalogue.xlsx's Source column references them. Send both (plus the latest scaffold and safeguarding note) before the call below.
Governance | Schedule stakeholder call with Arshad | Open | High | Murtaza | — | New (14 Sep 2026): Arshad wants to meet ASAP (same day if possible) to run through everything and line up next steps. Confirm a time and agenda: iGCSE dual-board effort/timeline, marking-review staffing (row 25), final sign-off authority (row 27), pilot budget/timeline (row 28).
Governance | P-1 Marking-review staffing (now A-Level only) — who, how many, cost | Open | High | Arshad | — | New (21 Sep 2026, Baseline v1.0). Needed before A-Level go-live. Scope is now much smaller: A-Level long answers only (48h turnaround), plus GCSE/iGCSE exceptions (F-10).
Governance | P-2 Owner and budget for the examiner-marked gold set (≥2,000 answers across both iGCSE boards + GCSE) | Open | High | Arshad | — | New (21 Sep 2026). Needed before pilot build starts — the ≥95% pilot KPI cannot be measured without it (Q-01, Q-03).
Commercial | P-8 Product name ("Study Loop" is a placeholder) | Open | Low | Arshad | — | New (21 Sep 2026). Needed before the marketing site build.
Technical | P-9 UK-only hosting requirement for schools (Hetzner is EU) | Open | Medium | Arshad / pilot schools | — | New (21 Sep 2026). Needed before first school signs. If required, Hetzner has no UK region — would need a UK provider for the school tenant.
Governance | P-10 Final design reference: HTML prototype/PDF vs rebuild in Figma | Open | Medium | Murtaza + Arshad | — | New (21 Sep 2026). Needed before engineering handoff. Prototype is at 121 screens; Arshad has the mockups and is reviewing.
Governance | Obtain sign-off on Requirements Baseline v1.0 | Open | High | Arshad | P-7 | New (21 Sep 2026). Requirements_Baseline_v1.0_LOCKED.docx §12. From sign-off onward, scope changes need a written change request.
Priority:
High
Medium
Low

## Decision Log
ID | Date | Decision | Decided by | Status | Source
D-01 | 14 Sep 2026 | LLM vendor: Anthropic Claude, direct API | Murtaza (Karsaaz) | Locked | Technical Architecture FINAL v2, §2 #1
D-02 | 14 Sep 2026 | Hosting: Self-hosted Docker (Hetzner-style) | Murtaza (Karsaaz) | Locked | Technical Architecture FINAL v2, §2 #2
D-03 | 14 Sep 2026 | Database: PostgreSQL for everything | Murtaza (Karsaaz) | Locked | Technical Architecture FINAL v2, §2 #3
D-04 | 14 Sep 2026 | Vector store: pgvector, same Postgres instance | Murtaza (Karsaaz) | Locked | Technical Architecture FINAL v2, §2 #4
D-05 | 14 Sep 2026 | Voice (STT/TTS): Google Cloud Speech (STT + TTS) | Murtaza (Karsaaz) | Locked | Technical Architecture FINAL v2, §2 #5
D-06 | 14 Sep 2026 | Vision / handwriting: Claude vision — no new vendor | Murtaza (Karsaaz) | Locked | Technical Architecture FINAL v2, §2 #6
D-07 | 14 Sep 2026 | Mobile: Native Swift (iOS) + Kotlin (Android) | Murtaza (Karsaaz) | Locked | Technical Architecture FINAL v2, §2 #7
D-08 | 14 Sep 2026 | Safety classifier: Second, independently prompted Claude call | Murtaza (Karsaaz) | Locked | Technical Architecture FINAL v2, §2 #8
D-09 | 14 Sep 2026 | Age assurance (OSA): Lightweight in-house, swappable interface | Murtaza (Karsaaz) | Locked | Technical Architecture FINAL v2, §2 #9
D-10 | 14 Sep 2026 | DBS checks: uCheck | Murtaza (Karsaaz) | Locked | Technical Architecture FINAL v2, §2 #10
D-11 | 14 Sep 2026 | Push notifications: OneSignal | Murtaza (Karsaaz) | Locked | Technical Architecture FINAL v2, §2 #11
D-12 | 14 Sep 2026 | Transactional email: Postmark | Murtaza (Karsaaz) | Locked | Technical Architecture FINAL v2, §2 #12
D-13 | 14 Sep 2026 | Event streaming: Redis Streams / direct DB for pilot; Kafka deferred | Murtaza (Karsaaz) | Locked | Technical Architecture FINAL v2, §2 #13
D-14 | 21 Sep 2026 | Standing rule: any requirement the client has stated is implemented, never removed. Streamlining applies only to items the delivery team added. | Murtaza (Karsaaz) | Locked | Requirements Baseline v1.0
D-15 | 21 Sep 2026 | AI drives the education layer only. No personal data (name, DOB, email, school, stable user ID) is sent to any AI vendor. All AI calls pass through an AI Gateway that tokenises requests and redacts free text and images. | Murtaza (Karsaaz) | Locked | Requirements Baseline v1.0
D-16 | 21 Sep 2026 | A-Level: AI-assisted marking with mandatory human review (client Round 1) — AI mark shown as provisional until a reviewer confirms. | Client (Round 1) | Locked | Requirements Baseline v1.0
D-17 | 21 Sep 2026 | GCSE / iGCSE: no routine human marking review. Exceptions only — low confidence, disagreement between two marking passes, or student dispute. | Murtaza (Karsaaz) | Locked | Requirements Baseline v1.0
D-18 | 21 Sep 2026 | AI question QC is automated (grounding, spec tag, mark-scheme consistency, duplicate, answerability); humans handle failures only. | Murtaza (Karsaaz) | Locked | Requirements Baseline v1.0
D-19 | 21 Sep 2026 | Marking accuracy (pilot success ≥95%) is measured per marking point against an examiner-marked gold set, reported by board and question type; prompts are promoted only if they beat the live version. | Murtaza (Karsaaz) | Locked — gold-set owner pending | Requirements Baseline v1.0
D-20 | 21 Sep 2026 | Voice is the one path where a vendor receives personal data (audio to Google Cloud Speech). Requires separate parent consent; transcripts retained 30 days and visible to parents. | Murtaza (Karsaaz) | Locked | Requirements Baseline v1.0
D-21 | 21 Sep 2026 | Gamification (badges, streaks, XP) held back to Phase 2 per client Round 1 and removed from MVP screens. | Client (Round 1) | Locked | Requirements Baseline v1.0
D-22 | 21 Sep 2026 | Business model: subscription (consumer) and per-pupil invoice (schools) at the same price tier; Stripe for both. | Client (Round 1) + Murtaza | Locked | Requirements Baseline v1.0
D-23 | 21 Sep 2026 | B2B scope for MVP adds assignments, class insights, MIS/CSV rostering, Google/Microsoft SSO, online DPA and invoice billing. | Client (Round 1: parallel launch) | Locked | Requirements Baseline v1.0
D-24 | 21 Sep 2026 | Embeddings for pgvector: a self-hosted open-source embedding model on our own server (Anthropic has no embeddings model). Only exam content is embedded, never learner data. | Murtaza (Karsaaz) | Locked | Question-generation design discussion
D-25 | 21 Sep 2026 | Question generation is bank-first: nightly batch generation through the 5 QC checks; on-demand generation only to top up thin spec points. | Murtaza (Karsaaz) | Locked | Question-generation design discussion
D-26 | 21 Sep 2026 | Calculation questions: Claude writes the template, our code computes every numeric answer and re-randomises values. The AI never computes numeric answers. | Murtaza (Karsaaz) | Locked | Question-generation design discussion
D-27 | 21 Sep 2026 | Diagrams in the MVP: reusable apparatus-diagram library plus code-drawn graphs from data. No AI-generated images. | Murtaza (Karsaaz) | Locked | Question-generation design discussion
D-28 | 21 Sep 2026 | Pilot runs on Claude (decision #1 unchanged). The AI Gateway is built model-agnostic: each task (marking, generation, tagging, QC, tutor, safety) routes to a configurable model. Self-hosted open models may replace Claude task by task later, only after passing the same gold-set gate (beats live version, ≥95%). Candidate order: batch generation/tagging/QC first, marking last. | Murtaza (Karsaaz) | Locked | Open-source LLM discussion
D-01 to D-13 = the 13 technology decisions (14 Sep 2026). D-14 to D-23 = Requirements Baseline v1.0 (21 Sep 2026). D-24 onward = AI-side design decisions. Client-round decisions from 4 Sep are recorded row-by-row on the Open Items Tracker sheet.