## Read Me
User Story Catalogue — Online Tutor Platform
Every feature and process across the full platform scope: the client's Development Brief v3 (Atom Learning-equivalent build + flagship AI question-generation engine + Cognito/Seneca/Tassomai/CENTURY-inspired improvements), and the AI Tutor Intelligence Layer brainstorm addendum (engagement controls, mastery engine, tiered marking, accessibility, safety).
How to use this
Sheet 2 ("User Stories") is the full backlog — one row per story, filterable by Epic, Role, Priority and Phase. Use the column filters (Data > AutoFilter is already on) to pull a view for sprint planning, e.g. filter Phase = "Pilot" and Priority = "Must" to see the true MVP scope for the Chemistry pilot.
Priority is MoSCoW (Must / Should / Could / Won't yet) and Phase maps to the 3-phase rollout already agreed in the brief and the brainstorm doc's Section 7. Both are starting judgement calls for your team to refine, not final — flag anything that looks wrong.
Roles
Visitor — Anyone browsing the marketing site pre-signup.
Parent — Account owner/billing payer; may also monitor a child's progress.
Student — The child using the learning product day-to-day.
Content Admin — Internal team managing the specification tree, style profiles, question review queue.
Marking Reviewer — Internal (or contracted) subject specialist reviewing AI-assisted long-form/A-Level marks.
Tutor — 1:1 tuition marketplace tutor (add-on service per brief Part 1).
Teacher / School Admin — B2B "Atom School"-equivalent channel — see Phase = "Deferred (B2B)".
Phases
Pilot — GCSE + iGCSE Chemistry, 1-2 subjects, all 5 GCSE boards — proves the core loop end to end.
Phase 2 — Widen to all subjects/boards; full mock-paper assembly; tiered marking incl. A-Level; predictive grading; parent narrative reports.
Phase 3 — Grade-targeted mastery loop; voice mode; DKT upgrade; gamification (post compliance review); full SEND differentiation; teacher dashboards if B2B is greenlit.
Deferred (B2B) — Schools/teacher channel — held until the consumer product and pilot are proven, per the Open Items Tracker.
Ongoing — Marketing, content ops and support — not phase-gated, runs continuously alongside build phases.
Related documents (same project folder)
• AI Learning_Website_Analysis_and_Dev_Brief_v3.docx — the client's full spec (source for most epics below).
• AI_Tutor_Intelligence_Layer_Brainstorm.docx — source for the engagement/mastery/marking/safety epics.
• GCSE_iGCSE_Chemistry_Pilot_Scaffold.xlsx — the topic/board detail behind the Pilot-phase content stories.
• content_model_schema.sql — the data model these stories are written against.
• Project_Open_Items_Tracker.xlsx — decisions this catalogue assumes are still open (see Priority/Phase notes).
v1.0 Requirements Lock (21 Sep 2026)
This catalogue now matches Requirements_Baseline_v1.0_LOCKED.docx. 31 new stories added (US-100 to US-130) and 15 existing stories revised; every change is explained in column I ("v1.0 Change"). Total: 130 stories.
Phases now follow the locked scope: B2B (US-095 to US-097) and voice (US-075) moved to Pilot per client Round 1; gamification (US-080) held to Phase 2; tutor marketplace relabelled "Deferred". The "Deferred (B2B)" phase described above no longer applies to schools.
A-Level stories (US-048, US-113, US-114) are tagged Phase 2 because A-Level is outside the Chemistry pilot, but they are part of the locked MVP scope (client Round 1: mandatory human review).
New role: Operations Reviewer (GCSE/iGCSE marking exceptions). New epic: Q. AI Operations & Quality. Pre-merge copy kept in _archive_pre_v1.0/.

## User Stories
ID | Epic | Role | User Story | Acceptance Notes | Priority | Phase | Source | v1.0 Change (21 Sep 2026)
US-001 | A. Marketing & Discovery | Visitor | Browse subject/qualification pages (11+, GCSE, iGCSE, A Level) to understand the offer before signing up. | Mega-menu IA per brief Section 3-4. | Must | Ongoing | Brief v3
US-002 | A. Marketing & Discovery | Visitor | Read an FAQ covering marking accuracy, exam boards covered, cost vs tutoring, and whether a parent is required. | 11 Q&As minimum per brief Section 4.5. | Must | Ongoing | Brief v3
US-003 | A. Marketing & Discovery | Visitor | Try one live, marked sample question directly on the homepage before registering. | Stronger proof point than screenshots. | Should | Phase 2 | Brief v3
US-004 | A. Marketing & Discovery | Visitor | Download a free lead-magnet resource (familiarisation pack, baseline test) in exchange for an email address. | Existing SEO/lead-gen pattern. | Should | Ongoing | Brief v3
US-005 | A. Marketing & Discovery | Visitor | See transparent, methodology-explained outcome statistics rather than one headline percentage. | Needs genuine before/after data collection built in from day one — see Open Items Tracker. | Should | Phase 2 | Brief v3
US-006 | A. Marketing & Discovery | Visitor | Read named case studies/testimonials with specific before/after scores (with permission). | Requires a consent/testimonial-collection process. | Could | Phase 2 | Brief v3
US-007 | A. Marketing & Discovery | Visitor | Find an exam-date calendar by region so I can plan revision timelines. | 11+ dates by region per brief Section 9. | Could | Ongoing | Brief v3
US-008 | A. Marketing & Discovery | Visitor | Take a short "which plan is right for us" quiz instead of parsing the full pricing matrix. | Reduces pricing-page complexity per brief Part 2, Section D. | Should | Phase 2 | Brief v3
US-009 | A. Marketing & Discovery | Visitor | Browse a free, publicly-accessible resource library (glossary, past-paper index) with no email gate. | Builds goodwill before conversion ask, per brief Part 2 Section E. | Could | Phase 3 | Brief v3
US-010 | B. Registration & Onboarding | Parent | Create an account to manage my child's subscription and progress. | Core account creation flow. | Must | Pilot | Brief v3
US-011 | B. Registration & Onboarding | Parent | Add multiple child profiles under one account. | One parent login, multiple children per brief Section 8. | Must | Pilot | Brief v3
US-012 | B. Registration & Onboarding | Student | Have my own profile under a parent account, or use the platform standalone without a parent present. | Standalone mode per brief Section 8. | Should | Phase 2 | Brief v3
US-013 | B. Registration & Onboarding | Student | Select qualification, exam board and subject(s) so content is tailored to what I'm actually sitting. | Data model = qualification x board x subject, per content_model_schema.sql. | Must | Pilot | Brief v3
US-014 | B. Registration & Onboarding | Student | Be asked what I want from this subject — exam prep, general study, target score, or a specific weak area — so my plan is tailored from day one. | Directly requested by the client in the original brief. | Must | Pilot | Brief v3
US-015 | B. Registration & Onboarding | Student | Take a short adaptive diagnostic/baseline test so the system knows my starting level. | IRT-based placement, see Brainstorm doc Section 4.2. | Must | Pilot | Brainstorm doc
US-016 | B. Registration & Onboarding | Student | Receive a personalised weekly revision plan generated from my subject/board/target exam date. | Adapts over time per brief Section 7. | Should | Phase 2 | Brief v3
US-017 | B. Registration & Onboarding | Parent | Set my child's target grade or score per subject so practice is pitched at the right stretch level. | Feeds grade-targeted stretch practice, brief Part 2. | Must | Pilot | Brief v3
US-018 | B. Registration & Onboarding | Student | Set accessibility preferences (dyslexia font, text size, TTS) during onboarding. | One-tap setting, not a separate product, per brief v3. | Should | Phase 3 | Brief v3
US-019 | C. Subscription & Billing | Parent | See a pricing page segmented by age/qualification/tier with a monthly/yearly toggle. | 3 tabs x year-group selector x tier cards, per brief Section 6. | Must | Phase 2 | Brief v3
US-020 | C. Subscription & Billing | Parent | Select subjects within my plan, including Combined Science as an alternative to the three separate sciences. | Combined Science is its own subject, not a bundle, per brief Section 2. | Must | Pilot | Brief v3
US-021 | C. Subscription & Billing | Parent | Try the platform on a free trial before committing to a paid plan. | Core conversion funnel. | Must | Pilot | Brief v3
US-022 | C. Subscription & Billing | Parent | Have a sibling/multi-child discount applied automatically. | Family pricing, brief Part 2 Section B. | Should | Phase 2 | Brief v3
US-023 | C. Subscription & Billing | Parent | Upgrade, downgrade or change subjects mid-subscription. | Standard SaaS account-management need. | Should | Phase 2 | Brief v3
US-024 | C. Subscription & Billing | Parent | Buy a lower-commitment single-subject/single-board micro-subscription. | Widens funnel below the full multi-subject tier, brief Part 2 Section F. | Could | Phase 3 | Brief v3
US-025 | C. Subscription & Billing | Parent | See exactly what's included/excluded per tier (e.g. mock tests) before paying. | Feature checklist per plan card, brief Section 6. | Must | Phase 2 | Brief v3
US-026 | C. Subscription & Billing | Parent | Refer a friend and receive a reward. | Referral programme, brief Section 9. | Could | Phase 3 | Brief v3
US-027 | D. Practice & Question Delivery | Student | Get unlimited practice questions per topic so I never run out of material. | Core promise, brief Section 7. | Must | Pilot | Brief v3
US-028 | D. Practice & Question Delivery | Student | Request a full mock paper matching the real exam's structure, timing and topic weighting. | Assembled from AI-generated + real questions, brief Part 2. | Should | Phase 2 | Brief v3
US-029 | D. Practice & Question Delivery | Student | See real past-paper questions clearly labelled "from [board] [year] paper" vs AI-generated ones. | Authenticity/trust requirement, brief v3. | Must | Pilot | Brief v3
US-030 | D. Practice & Question Delivery | Student | Sit a genuinely adaptive 11+ entrance test with no skip and no going back, matching real exam behaviour. | Interaction-rule requirement, brief v3. | Could | Phase 3 | Brief v3
US-031 | D. Practice & Question Delivery | Student | Request several versions of the same topic/difficulty in one go, with numbers re-randomised for maths. | Prevents answers being passed from memory, brief v3. | Should | Phase 2 | Brief v3
US-032 | D. Practice & Question Delivery | Student | Answer by typing, speaking (auto-transcribed), or photographing handwritten working — all marked the same way. | Three input modes, brief v3; photo/speech need the vision/STT pipeline. | Should | Phase 2 | Brief v3
US-033 | D. Practice & Question Delivery | Student | Photograph a completed printed practice paper and get an instant score. | Already an Atom Learning feature to replicate, brief Section 7. | Should | Phase 2 | Brief v3
US-034 | D. Practice & Question Delivery | Student | Build my own mixed-topic quiz or mock from any combination of topics I've covered. | Cognito-inspired, brief v3. | Could | Phase 2 | Brief v3
US-035 | D. Practice & Question Delivery | Student | Have an achievable daily micro-goal (e.g. 10 questions) as the default rhythm, alongside unlimited practice for those who want more. | Tassomai "little and often" pattern, brief v3. | Should | Phase 2 | Brief v3
US-036 | D. Practice & Question Delivery | Student | Use a "wrong answers only" mode to redrill everything I've previously got wrong across a subject. | Seneca-inspired, brief v3. | Should | Phase 2 | Brief v3
US-037 | E. AI Question Generation | Platform | Ground every generated question in real past papers and mark schemes, per board, so style/difficulty is authentic. | Reference-library + Self-RAG grounding check, Brainstorm doc Section 5. | Must | Pilot | Brainstorm doc
US-038 | E. AI Question Generation | Platform | Keep a separate style profile per exam board so generated questions don't read identically across boards. | board_style_profile table in content_model_schema.sql. | Must | Pilot | Pilot scaffold
US-039 | E. AI Question Generation | Platform | Tag every question to its exact specification point, not just a broad topic name. | spec_topic hierarchy (topic_level 1-3) in content_model_schema.sql. | Must | Pilot | Pilot scaffold
US-040 | E. AI Question Generation | Platform | Supplement the question bank with reviewed, clearly-labelled material sourced from elsewhere online once the core bank is exhausted. | Must go through the same review/licensing lens as generated content — see Open Items Tracker. | Could | Phase 3 | Brief v3
US-041 | E. AI Question Generation | Content Admin | Review only the AI-generated questions that fail automated quality checks (grounding, spec tag, mark-scheme consistency, duplicate, answerability); passing questions publish automatically. | Automated 5-check QC per Requirements Baseline v1.0 §5.3; question.review_status set by the QC pipeline, not a sample review. | Must | Pilot | Brief v3 | REVISED: story reworded. Per D-18 automated 5-check QC; humans see failures only. Screen E-01 (revised). Superseded in detail by US-112.
US-042 | E. AI Question Generation | Student | Have the engine keep generating questions at my target grade for a topic until I'm consistently hitting it, then move me on. | Grade-targeted stretch practice loop, brief Part 2 Phase 3. | Should | Phase 3 | Brief v3
US-043 | E. AI Question Generation | Student | See an authentic past-paper look and feel (official layout, cover, numbering) when sitting a real paper. | brief v3 "authentic look and feel" requirement. | Could | Phase 2 | Brief v3
US-044 | F. Marking & Feedback | Student | Get instant, exam-aligned automatic marking with a per-question right/wrong + explanation. | Core promise, brief Section 7. | Must | Pilot | Brief v3
US-045 | F. Marking & Feedback | Student | See the full mark scheme, point by point, for how my answer was marked. | mark_scheme table in content_model_schema.sql. | Must | Pilot | Pilot scaffold
US-046 | F. Marking & Feedback | Student | Self-mark against a revealed mark scheme as an alternative to AI marking. | Cognito-inspired, brief v3. | Could | Phase 2 | Brief v3
US-047 | F. Marking & Feedback | Student | Flag "disagree with this mark" on any auto-marked question so it gets reviewed. | Routes the answer into F-10 Marking Exceptions; resolved disputes join the gold set. | Must | Pilot | Brief v3 | REVISED: Priority Should→Must; Phase Phase 2→Pilot. Student dispute is one of the three triggers for the GCSE/iGCSE exceptions queue (D-17), so it is needed at launch.
US-048 | F. Marking & Feedback | Marking Reviewer | Review every AI-marked A-Level long answer in an anonymised workbench, confirm or adjust the mark using the AI marking trail. | Mandatory for all A-Level long answers (client Round 1). 48h turnaround target. Adjusted marks feed the gold set. Screen F-05 (revised). | Must | Phase 2 | Brainstorm doc | REVISED: story reworded. Per D-16/D-17 — A-Level only, 100% reviewed, anonymised. GCSE/iGCSE exceptions move to US-115 / F-10. Detail in US-114.
US-049 | F. Marking & Feedback | Student | See a "this is an AI-assisted estimate, not an official mark" disclaimer on long-form A-Level marks. | Provisional label + review status + expected turnaround (Baseline §5.1). Does not count toward progress until confirmed. | Must | Phase 2 | Brainstorm doc | REVISED. A-Level mark shown as PROVISIONAL until reviewer confirms (F-09, US-113).
US-050 | F. Marking & Feedback | Student | Be re-explained a concept in a different format (diagram/worked example) if I get it wrong a second time, rather than the same explanation repeated. | Seneca-inspired, brief v3. | Should | Phase 2 | Brief v3
US-051 | F. Marking & Feedback | Student | Be prompted to explain my reasoning before the answer is revealed (Socratic explain-back), with targeted hints first. | Khanmigo-style pattern, Brainstorm doc Section 4.3. | Should | Phase 2 | Brainstorm doc
US-052 | F. Marking & Feedback | Student | Photograph a question I'm stuck on (not just a finished answer) and get a step-by-step walkthrough with hints revealed one at a time. | Photomath-inspired, brief v3. | Could | Phase 3 | Brief v3
US-053 | G. Engagement Intelligence | Student | Be offered a hint or a switch to a different topic if I stay too long on a question with no progress. | Behavioural telemetry + focus-shift, Brainstorm doc Section 4.1. | Must | Pilot | Brainstorm doc
US-054 | G. Engagement Intelligence | Student | Have the tutor notice frustration signals and respond with encouragement and a difficulty reset, rather than pushing harder. | "Confusion-rescue" pattern, Brainstorm doc Section 4.1. | Should | Pilot | Brainstorm doc
US-055 | G. Engagement Intelligence | Student | Receive occasional surprise short quizzes on topics I haven't touched recently. | Checks the system's belief about what I know is still accurate, Brainstorm doc Section 4.1. | Should | Phase 2 | Brainstorm doc
US-056 | G. Engagement Intelligence | Student | Be asked how confident I am before an answer is revealed. | Confidence calibration, Brainstorm doc Section 4.2. | Should | Pilot | Brainstorm doc
US-057 | G. Engagement Intelligence | Platform | Maintain a mastery model (BKT, graduating to DKT at scale) per student per topic. | mastery_state table in content_model_schema.sql. | Must | Pilot | Pilot scaffold
US-058 | G. Engagement Intelligence | Student | Have previously-mastered topics resurfaced on a spaced schedule so I don't forget them. | FSRS-based scheduling, Brainstorm doc Section 4.2. | Should | Phase 2 | Brainstorm doc
US-059 | G. Engagement Intelligence | Platform | Run an IRT-based adaptive placement test so a student's starting level is estimated from just a few questions. | Also backs Epic B's diagnostic test. | Must | Pilot | Brainstorm doc
US-060 | G. Engagement Intelligence | Student | Have the teaching style (direct instruction vs guided example vs full question) match my current mastery on that topic. | Pedagogical strategy controller, Brainstorm doc Section 4.2 — core integration layer. | Should | Phase 2 | Brainstorm doc
US-061 | H. Progress & Reporting | Parent | See a longitudinal progress dashboard (topic-level mastery, trend over time). | Core promise, brief Section 7. | Must | Pilot | Brief v3
US-062 | H. Progress & Reporting | Parent | See the specific misconception behind each wrong answer in plain English, not just a score. | brief Part 2 Section B "why transparency". | Should | Phase 2 | Brief v3
US-063 | H. Progress & Reporting | Parent | Receive a weekly AI-generated narrative summary (what improved, what's shaky, what's next). | Brainstorm doc Section 4.5. | Should | Phase 2 | Brainstorm doc
US-064 | H. Progress & Reporting | Parent | See a predicted grade band per subject with an honest confidence interval. | Combines mastery posterior + IRT ability estimate, Brainstorm doc Section 4.4. | Could | Phase 2 | Brainstorm doc
US-065 | H. Progress & Reporting | Parent | Get an early-warning alert when my child is drifting on a topic, before it becomes a bigger gap. | CENTURY Tech-inspired, brief v3. | Should | Phase 3 | Brief v3
US-066 | H. Progress & Reporting | Student | See a visual knowledge map/skill tree showing which topics are secure. | Tassomai "Tree"-inspired, brief v3. | Could | Phase 3 | Brief v3
US-067 | H. Progress & Reporting | Student | See anonymised cohort context (e.g. "top 20% this month") without any other student's identity exposed. | Brainstorm doc Section 4.5. | Could | Phase 3 | Brainstorm doc
US-068 | H. Progress & Reporting | Parent | Get a printable action-plan checklist after a diagnostic/session for offline use. | IXL-inspired, brief v3. | Could | Phase 2 | Brief v3
US-069 | I. Revision Content | Student | Get auto-generated flashcard decks per topic as a lighter revision mode. | brief Part 2, quick win. | Should | Phase 2 | Brief v3
US-070 | I. Revision Content | Student | Build my own custom flashcard deck. | brief Part 2. | Could | Phase 2 | Brief v3
US-071 | I. Revision Content | Student | Read short, AI-rewritten (original, non-copied) revision notes per topic. | Copyright-safe generation requirement, brief v3. | Should | Phase 2 | Brief v3
US-072 | I. Revision Content | Student | Get a one-page cheat sheet per topic/subject for last-minute review. | Cognito-inspired, brief v3. | Could | Phase 2 | Brief v3
US-073 | I. Revision Content | Student | Do a quick 2-minute knowledge-check quiz between longer practice sessions. | Cognito-inspired, brief v3. | Should | Phase 2 | Brief v3
US-074 | I. Revision Content | Student | Share a flashcard deck or quiz set with classmates or a study group. | Quizlet-inspired, brief v3. | Could | Phase 3 | Brief v3
US-075 | J. Voice & Accessibility | Student | Use a spoken-dialogue tutor mode to talk through a topic hands-free. | Skye/Amelia-inspired, brief v3 + Brainstorm doc Section 4.3. | Must | Pilot | Brainstorm doc | REVISED: Priority Could→Must; Phase Phase 3→Pilot. Client Round 1: voice mode from day 1. Consent + error states in US-118 / J-06.
US-076 | J. Voice & Accessibility | Student | As an English Language/Literature student, practise verbal discussion of a text/writer's intent aloud. | Matches how English is actually examined, brief v3. | Could | Phase 3 | Brainstorm doc
US-077 | J. Voice & Accessibility | Student | Use dyslexia-friendly fonts, adjustable spacing and colour/contrast settings. | brief v3 accessibility requirement. | Should | Phase 3 | Brief v3
US-078 | J. Voice & Accessibility | Student | Practise under extended-time simulation matching my real exam access arrangements. | Brainstorm doc Section 4.6. | Could | Phase 3 | Brainstorm doc
US-079 | J. Voice & Accessibility | Student | Toggle simplified-language question wording without the underlying content changing. | Brainstorm doc Section 4.6. | Could | Phase 3 | Brainstorm doc
US-080 | K. Motivation & Gamification | Student | Earn streaks and mastery badges tied to genuine topic progress, not just time-on-platform. | Brainstorm doc Section 4.6 — needs AADC-aware design review first. | Won't (MVP) | Phase 2 | Brainstorm doc | REVISED: Priority Could→Won't (MVP); Phase Phase 3→Phase 2. D-21: held back to Phase 2 per client Round 1 and removed from MVP screens (see US-130).
US-081 | K. Motivation & Gamification | Parent | Opt my child into a daily micro-goal nudge rather than have it on by default. | AADC nudge-technique caution, Open Items Tracker. | Should | Phase 3 | Brainstorm doc | REVISED. D-21: micro-goal kept without streak mechanics; nudge opt-in follows gamification to Phase 2.
US-082 | L. Safety & Compliance | Platform | Run a secondary monitoring model reviewing every tutor conversation in real time. | Khanmigo-pattern, Brainstorm doc Section 4.6. | Must | Pilot | Brainstorm doc
US-083 | L. Safety & Compliance | Platform | Refuse to do a student's homework verbatim, keeping the tool a practice engine, not an answer shortcut. | Brainstorm doc Section 4.6. | Must | Pilot | Brainstorm doc
US-084 | L. Safety & Compliance | Parent | Give explicit consent for my under-13 child's data collection. | UK GDPR/AADC requirement, Brainstorm doc Section 6. | Must | Pilot | Brainstorm doc
US-085 | L. Safety & Compliance | Platform | Default engagement-telemetry collection to high-privacy settings. | AADC "privacy by default" standard, Brainstorm doc Section 6. | Must | Pilot | Brainstorm doc
US-086 | L. Safety & Compliance | Parent | Request deletion of my child's data. | Right to erasure, UK GDPR. | Must | Phase 2 | Brainstorm doc
US-087 | M. Content Administration | Content Admin | Manage the specification/topic tree per qualification/board/subject as specs change. | spec_topic hierarchy, content_model_schema.sql. | Must | Pilot | Pilot scaffold
US-088 | M. Content Administration | Content Admin | Maintain each board's style profile (question wording, mark scheme format). | board_style_profile table, content_model_schema.sql. | Must | Pilot | Pilot scaffold
US-089 | M. Content Administration | Content Admin | Work through the queue of AI-generated questions that failed automated QC, fix or reject them. | Queue contains QC failures only (Baseline §5.3). | Must | Pilot | Pilot scaffold | REVISED: story reworded. Per D-18 — exceptions-only QC queue. Screen E-01 (revised).
US-090 | M. Content Administration | Content Admin | See all student "disagree with this mark" flags in one place to spot systemic marking issues. | Aggregates F-04 disputes and F-10 outcomes to spot systemic marking issues. | Should | Phase 2 | Pilot scaffold | REVISED. Flags now resolved individually in F-10; this dashboard is the aggregate view.
US-091 | M. Content Administration | Content Admin | Track which subjects/boards/qualifications still need spec-point-level tagging completed. | "Spec-Point Tag (fill in)" column, Pilot scaffold. | Must | Pilot | Pilot scaffold
US-092 | N. Tutor Marketplace | Parent | Browse and book a 1:1 tutor as an add-on to my subscription. | "Atom Tuition"-equivalent, brief Section 1. | Won't (yet) | Deferred | Brief v3 | REVISED: Phase Deferred (B2B)→Deferred. Tutor marketplace stays out of MVP scope (Baseline §10). Phase label changed because B2B is no longer deferred.
US-093 | N. Tutor Marketplace | Tutor | Create a profile and set my availability/subjects so parents can find and book me. | Marketplace/recruitment channel, brief Section 1. | Won't (yet) | Deferred | Brief v3 | REVISED: Phase Deferred (B2B)→Deferred. Tutor marketplace stays out of MVP scope (Baseline §10). Phase label changed because B2B is no longer deferred.
US-094 | N. Tutor Marketplace | Tutor | See a student's AI-tracked mastery data, with permission, before a session so I can target it efficiently. | Requires a consent/data-sharing model. | Won't (yet) | Deferred | Brief v3 | REVISED: Phase Deferred (B2B)→Deferred. Tutor marketplace stays out of MVP scope (Baseline §10). Phase label changed because B2B is no longer deferred.
US-095 | O. School / B2B Channel | Teacher | Manage a class of students and assign topics/homework. | "Atom School"-equivalent, brief Section 1. | Must | Pilot | Brief v3 | REVISED: Priority Won't (yet)→Must; Phase Deferred (B2B)→Pilot. D-23: B2B launches in parallel with consumer (client Round 1). Extended by US-119 to US-122.
US-096 | O. School / B2B Channel | School Admin | See a class-level dashboard of mastery and engagement. | Brainstorm doc Section 4.5 — conditional on B2B being pursued. | Must | Pilot | Brainstorm doc | REVISED: Priority Won't (yet)→Must; Phase Deferred (B2B)→Pilot. D-23: B2B launches in parallel with consumer (client Round 1). Extended by US-119 to US-122.
US-097 | O. School / B2B Channel | School Admin | Confirm the platform aligns with our KCSIE filtering/monitoring policy before school-premises use. | Open Items Tracker — deferred, blocked by the B2B channel decision. | Must | Pilot | Brainstorm doc | REVISED: Priority Won't (yet)→Must; Phase Deferred (B2B)→Pilot. D-23: B2B launches in parallel with consumer (client Round 1). Extended by US-119 to US-122.
US-098 | P. Support | Parent | Search a help centre/FAQ to self-serve common questions. | brief Section 9. | Should | Phase 2 | Brief v3
US-099 | P. Support | Parent | Use live chat for a quick answer to an account/billing issue. | Live chat widget observed on reference site, brief Section 10. | Could | Phase 2 | Brief v3
US-100 | B. Registration & Onboarding | Parent | Verify my email with a code before adding a child — so that the account is provably mine before any child data is stored. | Screen(s): B-10. | Must | Pilot | Req. Baseline v1.0 | NEW — Discovery gap
US-101 | B. Registration & Onboarding | 11+ learner | Log in with a picture PIN instead of an email and password — so that I can start practising without an adult typing for me. | Screen(s): B-11. | Must | Pilot | Req. Baseline v1.0 | NEW — Discovery gap
US-102 | Shell. Foundational | Parent, student or teacher | Log in on the web, reset my password and use Google or Microsoft sign-in — so that I can get back into my account without contacting support. | Screen(s): Shell-09. | Must | Pilot | Req. Baseline v1.0 | NEW — Discovery gap
US-103 | Shell. Foundational | Staff member, reviewer or school admin | Be required to use two-step verification — so that privileged access to learner data is protected. | Screen(s): Shell-09. | Must | Pilot | Req. Baseline v1.0 | NEW — Discovery gap
US-104 | Shell. Foundational | Visitor | Read plain-English terms, privacy and AI-data pages and choose which cookies to allow — so that I understand how my family's data is used before signing up. | Screen(s): Shell-10. | Must | Pilot | Req. Baseline v1.0 | NEW — Discovery gap (PECR / Children's Code)
US-105 | L. Safety & Compliance | Platform | Confirm the paying account holder is an adult using a swappable method — so that we meet OSA age-assurance duties once the legal opinion is final. | Screen(s): L-05. | Must | Pilot | Req. Baseline v1.0 | NEW — Locked Decision 9
US-106 | C. Subscription & Billing | Parent | Get a reminder before my free trial ends and cancel in two clicks — so that I'm never charged by surprise. | Screen(s): C-08. | Must | Pilot | Req. Baseline v1.0 | NEW — Discovery gap (DMCC Act 2024)
US-107 | C. Subscription & Billing | Parent | Be told when a payment fails and update my card while my child keeps access — so that a card problem doesn't interrupt revision. | Screen(s): C-09. | Must | Pilot | Req. Baseline v1.0 | NEW — Discovery gap
US-108 | C. Subscription & Billing | Parent with more than one child | See one bill for all children and download invoices — so that I can manage family costs in one place. | Screen(s): C-10. | Should | Pilot | Req. Baseline v1.0 | NEW — Discovery gap
US-109 | D. Practice & Question Delivery | Student | See my mock paper result broken down by topic with a targeted drill — so that I know exactly where marks were lost and what to do next. | Screen(s): D-11. | Must | Pilot | Req. Baseline v1.0 | NEW — Discovery gap
US-110 | D. Practice & Question Delivery | Chemistry student | Write equations with state symbols, give numeric answers with units and significant figures, and open a periodic table — so that my answers can be marked as accurately as an examiner would. | Screen(s): D-12. | Must | Pilot | Req. Baseline v1.0 | NEW — Pilot-critical: ≥95% marking accuracy
US-111 | E. AI Question Generation | Content team member | Author questions with mark schemes and import past papers with spec tags and licence status — so that the bank is grounded in real exam style and licence-safe (no PMT material). | Screen(s): E-02. | Must | Pilot | Req. Baseline v1.0 | NEW — Client: off PMT; licensing pending
US-112 | E. AI Question Generation | Content team member | See only generated questions that fail automated quality checks — so that human effort is spent on exceptions, not on every question. | Screen(s): E-01 (revised). | Must | Pilot | Req. Baseline v1.0 | NEW — v1.0 streamlining
US-113 | F. Marking & Feedback | A-Level student | See my AI mark labelled provisional with review status and expected turnaround — so that I know the mark will be confirmed by a qualified reviewer. | Screen(s): F-09. A-Level go-live (A-Level is outside the Chemistry pilot). | Must | Phase 2 | Req. Baseline v1.0 | NEW — Client Round 1: A-Level mandatory human review
US-114 | F. Marking & Feedback | A-Level reviewer | Confirm or adjust the AI mark using its marking trail, without seeing the student's identity — so that every A-Level mark is examiner-quality and reviews stay unbiased. | Screen(s): F-05 (revised). A-Level go-live (A-Level is outside the Chemistry pilot). | Must | Phase 2 | Req. Baseline v1.0 | NEW — Client Round 1: A-Level mandatory human review
US-115 | F. Marking & Feedback | Operations reviewer | Resolve only GCSE/iGCSE answers that were low-confidence, where two marking passes disagreed, or that a student disputed — so that marking stays trustworthy without a routine review queue. | Screen(s): F-10. | Must | Pilot | Req. Baseline v1.0 | NEW — v1.0 streamlining
US-116 | H. Progress & Reporting | Parent | Switch voice and chat on or off, set time limits and quiet hours, and read my child's AI tutor conversations — so that I stay in control of how my child uses AI. | Screen(s): H-09. | Must | Pilot | Req. Baseline v1.0 | NEW — Discovery gap (safeguarding / transparency)
US-117 | H. Progress & Reporting | Parent | See my children's progress and reports in the mobile app — so that I can check in without a laptop. | Screen(s): H-10. | Must | Pilot | Req. Baseline v1.0 | NEW — Client Round 1: app + web in MVP
US-118 | J. Voice & Accessibility | Parent / student | Give separate consent for voice, and see clear microphone and connection errors with a text fallback — so that voice mode is safe, transparent and never a dead end. | Screen(s): J-06. | Must | Pilot | Req. Baseline v1.0 | NEW — Client Round 1: voice from day 1
US-119 | O. School / B2B Channel | Teacher | Set adaptive homework for a class with due dates and track completion — so that the platform fits how I already teach. | Screen(s): O-04. | Must | Pilot | Req. Baseline v1.0 | NEW — Client Round 1: B2B parallel launch
US-120 | O. School / B2B Channel | Teacher | See a class misconception heatmap and drill into any pupil — so that I can target re-teaching where it matters. | Screen(s): O-05. | Must | Pilot | Req. Baseline v1.0 | NEW — Client Round 1: B2B parallel launch
US-121 | O. School / B2B Channel | School admin | Import pupils and classes from our MIS or a CSV and enable Google/Microsoft SSO — so that onboarding a whole school takes minutes, not days. | Screen(s): O-06. | Must | Pilot | Req. Baseline v1.0 | NEW — Client Round 1: B2B parallel launch
US-122 | O. School / B2B Channel | School business manager | Sign the DPA online and pay by invoice and purchase order — so that we can buy through normal school procurement. | Screen(s): O-07. | Must | Pilot | Req. Baseline v1.0 | NEW — Client: same pricing; per-school DPA
US-123 | P. Support | Support agent | Look up an account, issue a refund or send a password reset without seeing learning content — so that I can help families quickly while protecting learner privacy. | Screen(s): P-03. | Must | Pilot | Req. Baseline v1.0 | NEW — Discovery gap
US-124 | P. Support | Compliance lead | See an append-only log of every privileged action — so that we can evidence who did what to whose data. | Screen(s): P-04. | Must | Pilot | Req. Baseline v1.0 | NEW — Discovery gap
US-125 | Q. AI Operations & Quality | Product owner | See marking accuracy against the examiner-marked gold set by board and question type — so that we can prove the ≥95% pilot success criterion. | Screen(s): Q-01. | Must | Pilot | Req. Baseline v1.0 | NEW — Client Round 1: pilot success = accuracy >95%
US-126 | Q. AI Operations & Quality | Data protection lead | Verify that no personal data reaches any AI vendor and review every redaction — so that our AI data boundary is auditable. | Screen(s): Q-02. | Must | Pilot | Req. Baseline v1.0 | NEW — v1.0: no personal data to any AI
US-127 | Q. AI Operations & Quality | AI engineer | Version prompts and promote one only when it beats the live version on the gold set — so that marking quality can only go up. | Screen(s): Q-03. | Must | Pilot | Req. Baseline v1.0 | NEW — v1.0 streamlining
US-128 | Q. AI Operations & Quality | Business owner | See AI cost per active student broken down by task — so that the subscription price stays profitable with voice enabled. | Screen(s): Q-04. | Should | Pilot | Req. Baseline v1.0 | NEW — Discovery gap (unit economics)
US-129 | Q. AI Operations & Quality | Safeguarding lead | Review AI safety-classifier flags and escalate concerns to the DSL — so that risks raised in AI conversations are acted on. | Screen(s): Q-05. | Must | Pilot | Req. Baseline v1.0 | NEW — Locked Decision 8
US-130 | K. Motivation & Gamification | Product owner | Hold badges, streaks and XP back to Phase 2 and remove them from MVP screens — so that the MVP matches the client's decision to hold gamification back. | Screen(s): K-01, D-08, Shell-01 (revised). | Won't (MVP) | Phase 2 | Req. Baseline v1.0 | NEW — Client Round 1: gamification held back